## Sheet1
Feature | Details | Developers | Due date | Acceptance Criteria | User Story
operational Pantry Quest DB | Write .sql file to create database tables with attributes, primary keys, and foreign keys based strictly off of ER diagram. | Karoline | 2014-10-22 | Tables and attributes in the ER diagram have been instantiated in .sql file with no errors. Attributes that are primary and foreign keys have been checked for compatibility (i.e. same type, name, purpose) with corresponding tables. | S001
Input Pantry Items (data for testing) (DB) | Insert values into DB (i.e. ingredients, recipes and corresponding info, filters) that can be used to begin writing SQL queries. | Brandon G. (Nariana, Michael, Karoline) | 2014-10-25 | 5-10 recipes have been inserted into Recipe table, with corresponding filters and recipe connections. Ingredients required for recipes, plus 10 unused ingredients have been inserted into Ingredients table. No errors occur when .sql file is run in MySQL. | S002
Create calls to Yumli/Big Oven API to populate (DB) | Use the calls to Yumli/Big Oven API to populate DB. Decode JSON from Yumli. | Nariana (Brandon G., Michael, Karoline) | 2014-10-26 | Recipes from Yumli have been added to the database. Made sucessfull calls to the API and stored the results in the DB. | S002
Implement algorithm for ranked search results based on matches with ingredients (DB) | Return recipies based on number of matching essential ingredients, vs matching substitutable ingredients. | Karoline (Nariana, Brandon G., Michael) | 2014-10-27 | Recipies are not just returned based on ranking or random order. There is a ratio of the number of matching essential ingredients, disregarding substitutables and non essentials. | S011
Basic return queries | Create simple queries to show data in database that can later be built upon for more complex queries related to user results. | Michael (Nariana, Brandon G. Karoline) | 2014-10-27 | Return accurate results for the following queries: 1. Return recipes with a particular ingredient 2. Return vegetarian recipes 3. Return something with carrots and cabbage that is vegetarian (This list is not limited to the following, but this is a good start.) | S011
Input Pantry Items (GUI) | Create basic GUI framework with text and search boxes that allows user to input and see selected ingredients and filter. | Brandon C. (Jacob, Tom) | 2014-10-25 | User is able to enter ingredients by text and check input. User is able to see ingredients and filters entered. | S002
User Interface templates (GUI) | Home screen (add ingredients), Search Results screen, and Recipe Instructions Screen: BASIC TEMPLATES for each screen + simple style | Jacob (Brandon C., Tom) | 2014-10-25 | Basic Layout of every page in our app is set. The user will understand how the web app looks |  | Iter1 Due Date: Nov 2